## Sheet1
Project Name | Deep learning-based road segmentation using aerial imagery for automated change detection
Project Acronym | RChan
Project Manager | Adian Dawuda
Project Deliverable | Model, Code and Paper/Documentation
Start Date | 2023-03-07
End Date | 2023-06-30
Overall Progress | 30%
WP | Time Estimate (hours) | Tasks | Responsible | Start | End | Status | KW10 | KW11 | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22 | KW23 | KW24 | KW25 | KW26
1 | 30 (10%) | Project Management
1.1 | 10 | Project overview (Gantt chart, Pert chart, risk analysis) | Adian | KW10 | KW26 | In progress |  |  |  | ▪ |  | ▪ |  | ▪ |  | ▪ |  | ▪ |  | ▪ |  | ▪ | ▪ | ▪ | Deliverable
1.2 | 3 | Time logging | Adian | KW10 | KW26 | In progress | [16 empty] | ▪ | ▫ | Milestone
1.3 | 17 | GitLab management | Adian | KW10 | KW26 | In progress | [16 empty] | ▪ |  | WP Duration
2 | 30 (10%) | Literature Review & Methodology | [22 empty] | WT Duration
2.1 | 18 | State of the art literature review | Adian | KW10 | KW14 | Completed |  |  |  |  | ▫
2.2 | 2 | Integration to Mendely | Adian | KW10 | KW14 | Completed |  |  |  |  | ▪
2.3 | 10 | Identifying methodology (incl choosing model architecture) | Adian | KW10 | KW14 | Completed |  |  |  |  | ▫
3 | 30 (10%) | Data Aquisition
3.1 | 10 | Obtaining training dataset | Adian | KW11 | KW13 | Completed |  |  |  | ▪
3.2 | 20 | Creating test dataset | Adian | KW11 | KW15 | In progress | [5 empty] | ▪
4 | 60 (20%) | Data Analysis
4.1 | 5 | Setting up computing environment | Adian | KW13 | KW14 | Completed |  |  |  |  | ▫
4.2 | 15 | Data cleaning/preprocessing | Adian | KW14 | KW18 | In progress | [8 empty] | ▪
4.3 | 30 | Building the model | Adian | KW14 | KW18 | In progress | [8 empty] | ▪
4.4 | 10 | Postprocessing | Adian | KW14 | KW18 | In progress | [8 empty] | ▪
5 | 60 (20%) | Testing, Evaluation, Validation
5.1 | 40 | Testing and interpreting the results | Adian | KW19 | KW22 | Not started | [9 empty] | ▫ | ▫ | ▫ | ▫
5.2 | 20 | Adjusting model and data | Adian | KW19 | KW22 | Not started | [9 empty] | ▪ | ▪ | ▪ | ▪
6 | 90 (30%) | Dissemination
6.1 | 50 | Writing Paper | Adian | KW19 | KW25 | Not started | [15 empty] | ▪
6.2 | 10 | Creating Poster | Adian | KW23 | KW25 | Not started | [15 empty] | ▪
6.3 | 20 | Creating Presentations | Adian | KW17 | KW25 | Not started | [9 empty] | ▪ | [5 empty] | ▪
6.4 | 10 | Publishing Code | Adian | KW23 | KW25 | Not started | [15 empty] | ▪
|  | Completion |  |  | KW26